## Sheet1
| Hazard Owner | Before Mitigation |  |  | Proposed Mitigation |  |  |  |  | After Mitigation
|  | Consequence | Probability | Risk Score |  | Due Date | Mitigation Owner | Mitigation Implemented | Mitigation Reviewer | Consequence | Probability | Risk Score
Company Risk
Company leadership is unaccountable for AWS engineering | <Board member name> | 4 | 3 | 1 | Company board member assigned as accountable for ethical AWS development. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name> | 4 | 3 | 1
Company ethical guidelines on AWS engineering are absent | <Employee name> |  |  |  | Publish internal engineering policy on the ethical AWS development and invite feedback from engineers working on AWS. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
Company conformance to ethical AWS engineering decays over time | <Employee name> |  |  |  | Annual rebaseline of company' ethical engineering policy to industry and Legal developments. Independent review and ratification by the company board strictly required. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
[5 empty] | Annual forum (at minimum) discussing ethical obligation of AWS engineers | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
AWS Risk
AWS are developed without 'meaningful human control risking 'escalation of conflicts outside the decisions by political and military leadership' | <Employee name> |  |  |  | Set internal definition for 'meaningful human control'. AWS projects shall include of semi-autonomous and autonomous vehicle. They must be evaluated for compliance to this definition of 'meaningful human control' no later than TRL gate 6. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
[5 empty] | Predictability of AWS shall be asses with confidence levels with respect to specified contexts and cirumstances of use. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
[5 empty] | Convene' joint workshop with stakeholders to assess a project's compliance to that definition at project kick off and at the production readiness review gate via a Failure Mode Effects and Criticality Analysis (FMECA) at a minimum. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
AWS accountability is compromised: risking misuse by nefarious actors, or contributing to 'obfuscated and non-attributable attack's. | <Employee name> |  |  |  | Define system integrity requirements that log AWS use and by whom. Define requirements that prevent modification or destruction of these logs.. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
[5 empty] | Add these system integrity requirements to all AWS projects at kickoff. | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
[5 empty] | Define system integrity requirements that require privileged logins to restrict use to authorised individuals and lock out functionality for each role type | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>
AWS are obtained by non-military actors such as police and private security risking civil rights decay particularly by 'despots to retain control over a population'. | <Employee name> |  |  |  | All AWS exports shall be government approved. All exports of civilian autonomous systems shall be reviewed | <Date> | <Employee Name> | <Mitigation X>, <Ref: 123> | <Employee Name>